## Test Matrix
Test ID | System | Persona | Scenario | Automated Bruno Request | Preconditions | Expected Result | Actual Result | Status | Severity | Ride ID | Driver ID | Tester | Device | Date | Time | Evidence Link | Notes
MAP-001 | DiddiMap | Developer | Health check | 09-DiddiMap-MVP/01 DiddiMap Health | DiddiMap staging deployed | HTTP 200, status ok | 200 OK, 351 ms | Pass |  |  |  | Codex | Bruno CLI | 2026-08-28
MAP-002 | DiddiMap | Developer | Database health | 09-DiddiMap-MVP/02 DiddiMap DB Health | PostGIS reachable | HTTP 200, database available | 200 OK, 461 ms | Pass |  |  |  | Codex | Bruno CLI | 2026-08-28
MAP-003 | DiddiMap | Developer | Autocomplete Plateau with bias | 09-DiddiMap-MVP/03 Autocomplete Plateau | DiddiMap data loaded | HTTP 200, results array, no 500 | 200 OK, 611 ms | Pass |  |  |  | Codex | Bruno CLI | 2026-08-28
MAP-004 | DiddiMap | Developer | Search Anador with bias | 09-DiddiMap-MVP/04 Geocoding Search Anador | DiddiMap data loaded | HTTP 200, list candidates | 200 OK, 622 ms | Pass |  |  |  | Codex | Bruno CLI | 2026-08-28
MAP-005 | DiddiMap | Developer | Route Yopougon to Plateau | 09-DiddiMap-MVP/05 Route Yopougon To Plateau | OSRM available | HTTP 200, LineString, plausible distance/duration | 200 OK, 420 ms | Pass |  |  |  | Codex | Bruno CLI | 2026-08-28
MAP-006 | DiddiMap | Developer | Route proposals detail | 09-DiddiMap-MVP/06 Route Proposals Detail | OSRM and enrichment available | HTTP 200, proposals with score breakdown | 200 OK, 2730 ms | Pass |  |  |  | Codex | Bruno CLI | 2026-08-28
MAP-007 | DiddiMap | Developer | Road search | 09-DiddiMap-MVP/07 Roads Search | DiddiMap data loaded | HTTP 200, no crash | 200 OK, 1146 ms | Pass |  |  |  | Codex | Bruno CLI | 2026-08-28
GO-000 | DiddiGo | Developer | Health check | 00-Health/01 Health | DiddiGo staging deployed | HTTP 200, status ok | 200 OK, 658 ms | Pass |  |  |  | Codex | Bruno CLI | 2026-08-28
GO-001 | DiddiGo | Developer | DiddiGo place search through DiddiMap | 10-MVP-Field-Test/01 DiddiGo Places Through DiddiMap | Passenger token available | HTTP 200, label/lat/lng candidates |  | Not Run
GO-002 | DiddiGo | Developer | DiddiGo pricing via DiddiMap | 10-MVP-Field-Test/02 DiddiGo Pricing Yopougon Plateau | Passenger token available | HTTP 200, fare/distance/duration/commission |  | Not Run
GO-003 | DiddiGo | Developer | DiddiGo creates route-dependent ride | 10-MVP-Field-Test/03 DiddiGo Route Dependent Ride Create | Passenger token; optional online driver | HTTP 201 or documented business error |  | Not Run
GO-004 | DiddiGo | Developer | Full happy path | Existing folders 01 to 08 | Passenger/driver/admin tokens; KYC approved; driver online | Ride completed and cash collected |  | Not Run
QA-001 | DiddiMap | Passenger | Search common destination in app | Manual | Frontend connected to staging | Useful nearby suggestions in under 1 second |  | Not Run
QA-002 | DiddiMap | Passenger | Search uncommon local landmark | Manual | Frontend connected to staging | Either useful result or clear not-found behavior |  | Not Run
QA-003 | DiddiMap | Driver | Route looks reasonable to local driver | Manual | Known Abidjan route selected | Driver judges route acceptable |  | Not Run
QA-004 | DiddiGo | Passenger | Create ride near online driver | Manual | Approved online driver within matching radius | Ride created and driver offer sent |  | Not Run
QA-005 | DiddiGo | Driver | Receive and accept ride offer | Manual | Driver app active with WebSocket | Offer visible and accept succeeds |  | Not Run
QA-006 | DiddiGo | Driver | Decline offer and reoffer | Manual | At least two eligible drivers online | Next eligible driver receives offer or no_driver_found |  | Not Run
QA-007 | DiddiGo | Passenger | Track driver live location | Manual | Driver sends location every 3-5 seconds | Passenger sees moving driver marker |  | Not Run
QA-008 | DiddiGo | Passenger | Share ride public link | Manual | Ride matched/in_progress | Public link opens without login and exposes no sensitive data |  | Not Run
QA-009 | DiddiGo | Passenger/Driver | Trigger emergency | Manual | Active ride | Emergency status open and backend log visible |  | Not Run
QA-010 | DiddiGo | Driver | Complete ride and confirm cash | Manual | Ride in_progress | Ride completed and payment collected |  | Not Run

## Summary
DiddiGo + DiddiMap MVP Field Test
Total tests | 22 | Wave 1 Goal | Stabilize the current MVP before advanced PRD features
Pass | 8 | Developer tests | Bruno validates API contracts and integrations
Fail | 0 | Human QA | Testers judge usefulness, UX, and field reality
Blocked | 0 | Critical evidence | ride_id, driver_id, timestamp, screenshot/log
Needs Review | 0 | Decision | Ship pilot only if P0/P1 blockers are closed
Not Run | 14 | Owner | Backend + Frontend + QA + Field coordinator
Pass rate | 36.36%

## Exit Criteria
ID | Exit criterion | Status | Notes
EC-001 | DiddiMap health and DB health pass | Not Run
EC-002 | DiddiMap route tests pass for common Abidjan trips | Not Run
EC-003 | DiddiGo places/pricing can reach DiddiMap | Not Run
EC-004 | Approved drivers can go online | Not Run
EC-005 | Nearby eligible driver receives offer | Not Run
EC-006 | Passenger and driver complete one cash ride | Not Run
EC-007 | Share link opens without login and hides sensitive data | Not Run
EC-008 | Emergency event is recorded and visible in logs | Not Run
EC-009 | No undocumented 500 appears during the core flow | Not Run